## ProjectPlan
Overalltime = 37 Weeks and 4 Days | [6 empty] | Overview: | not fixed |  | running |  | done
Phase | Work-Item Number | Work Items | Description | Dependability on other Work Items | Acceptance Criteria | Notes | Deadline | Juli |  |  | August |  |  |  |  | September |  |  |  | Oktober |  |  |  | November |  |  |  | Dezember |  |  |  |  | Januar |  |  |  | Februar |  |  |  |  | März |  |  | April | Mai
[8 empty] | KW 28 | KW 29 | KW 30 | KW 31 | KW 32 | KW 33 | KW 34 | KW 35 | KW 36 | KW 37 | KW 38 | KW 39 | KW 40 | KW 41 | KW 42 | KW 43 | KW 44 | KW 45 | KW 46 | KW 47 | KW 48 | KW 49 | KW 50 | KW 51 | KW 52 | KW 1 | KW 2 | KW 3 | KW 4 | KW 5 | KW 6 | KW 7 | KW 8 | KW 9 | KW 10 | KW 11 | KW 12 | KW 13
1. Pre-Planing | 1 | Write down Work Items / Things To-Do | Specially Phase 3. Pre-Development is hard to plan
| 2 | Job Offer Research | You want to apply for a remote job as Java developer. What are companies looking for? What kind of technologies, skills etc.? - Maven - Spring Framework - Junit / TDD - MongoDB - Azure Cloud - SOLID, Clean Software, Refactoring - Design Patterns - RESTful |  | - List which skills, technologies companies looking for | bar: Juli KW 28
| 3 | Create Timeline |  |  | - Timeline done until final deadline | bar: Juli KW 29 to August KW 32
| 4 | Insert intermidiate results, deadlines, goals | Connect your deadlines with things you enjoy | 3 | - Intermediate deadline + things which motivates me set | bar: Juli KW 30
| 5 | Write down your Motivation | To keep the motivation high, write down things you really want to do, things you enjoy as rewards on the long-haul. - Spa Day - Schweinshaxe - Sonos Musikbox - Snickers - Crossfit - Grey Hoodie from Asket - Day-Off - Jeans - Wellenwerk Besuch - Weiterbildung (Crossfit Level 1, Embedded Software Entwicklung) |  | - List of things which motivates me | bar: Juli KW 30
| 6 | Chose your Tools | What IDE? Set-up your Tools - InteliJ - Azure DevOps - Git Bash - JUnit - Which database / what IDE for databases? |  | - IntelliJ running - Azure DevOps running - JUnit running in IntelliJ - IDE Extension / separate IDE for Database development | Connection to Azure DevOps / Git is integrated into IntelliJ. Git Bash is not really needed | bar: Juli KW 30
| 7 | Follow some developers on Instagram to get good hints
2. Planing | 8 | Identification of User | Perform Use-Case Analysis: Step 1. |  | - List of user | bar: Juli KW 30
| 9 | Identification of Scenarios | Perform Use-Case Analysis: Step 2. | 8 | - List of scenarios | bar: Juli KW 30
| 10 | Identification of Use-Cases | Perform Use-Case Analysis: Step 3. | 9 | - List of use-cases | bar: August KW 31
| 11 | Create Features out of Use-Cases | Done in Azure DevOps | 10
| 12 | Break down features into User-Stories |  | 11
| 13 | Break down User-Stories into Tasks |  | 12
3. Pre-Development | 14 | Get familiar with TDD and JUnit | How to create Unit Test considering requirements? | 6, 10 | Write a small calcuator application and tests for it | Really Really small app; visualizes the TDD process and Junit |  | September KW 37: Asket Grey Hoodie
| 15 | Get familiar with SOLID | SRP, OCP, LSP, ISP, DIP understanding and example | 6 | Write 2 examples for each principle | In the end I just did one up to two examples for each principle | bar: August KW 33 to August KW 34
| 16 | Get familiar with Design Patterns |  | 6 | 3 x Creational, 3x Structural, 4x Behavioral in addition to already known Design Patterns | 1 Behavirol Pattern missing |  | August KW 35: Sommer-special bei Berlin Barbel
| 17 | Get familiar with Databases |  | 6
| 18 | Get familiar with Maven |  | 6 | bar: Oktober KW 40
| 19 | Get familiar with Spring Framework |  | 6
| 20 | Get familiar with creating websites (e.g. HTML) |  |  | Create Website existing out of three pages
| 21 | Get familiar with Hosting / Uploading Websites etc. |  | 20 | Upload Website from Work-Item 20 |  |  | Oktober KW 42: Spa Day
| 22 | Get familiar with CI/CD for websites |  | 20, 21 | Create Pipeline for Website from Work-Item 20. Writing code leads to new deployment |  |  | Dezember KW 49: Sonos Musikbox
4. Development |  | Create Architecture | considering SOLID and Design Pattern | 3. PreDevelopment
|  | Write Tests according to TDD |  | 14, 10
|  | Develop Website | Get User-Stories done

## Ziele
S | spezifisch | 50 Vokabeln lernen
M | messbar | Woher weiß ich wann ich mein Ziel erreicht habe? In dem Fall, wenn ich die 50 Vokabeln auswendig kann.
A | erreichbar | Habe ich heute überhaupt die Zeit 50 Vokabeln zu lernen?
R | realistisch | Kann ich überhaupt 50 Vokabeln lernen ohne ein Superhirn zu besitzen?
T | terminiert | Bis 18 Uhr will ich das geschafft haben